## Risk log
Risk Register
Project name: IWS Project
Project manager: Jabaran Khan
ID | Date raised | Risk description | Likelihood of the risk occurring | Impact if the risk occurs | Severity Rating based on impact & likelihood. | Owner Person who will manage the risk. | Mitigating action Actions to mitigate the risk e.g. reduce the likelihood. | Contingent action Action to be taken if the risk happens. | Progress on actions
1 | 2022-07-04 | Not having the code function correctly | Medium | High | High | Me - Project Lead | Import the skeleton code from the project specification and ensure that it works with my system | Discuss with tutors if any issues have occurred during implentation. | Keeping checking and testing certain aspects of it. No issues have arisen so far.
2 | 2022-07-04 | Project design and deliverable definition is incomplete. | Medium | High | Medium | Me - Project Lead | Ensure that testing is done and no major bugs are outstanding | Keep testing the codes in intervals and ensure that it can be troubleshooted | Systems are working fine but will keep testing to ensure stability
3 | 2022-07-04 | Check if the extensions can be added | Low | Low | Low | Me - Project Lead | Add additional aspects of code to the user project to further highlight coding ability | Ensure the project specification has been reached before adding this action | Project is still in progress and will see nearer the deadline to see if it works
| 2022-07-04 | Internet issues | Low | High | High | Me - Project Lead | Have back ups on Git as well as seeing alternative means of getting onto the internet | Contact trainers and discuss further options | No issues so far
4 | 2022-07-04 | Ensure full understanding of the code that is being implemented and that when it is delievered. | Medium | Medium | High | Me - Project Lead | Code can be explained on why it was implemented and what steps to were taken to do so. | Review code and leave comments on there so that it can be reviewed and checked by colleagues if desired | Everything has been understood so far and will keep reviewing in future
5 | 2022-07-04 | Getting burnt out | Medium | High | High | Me - Project Lead | Taking breaks when I can and as do not want to be burnt out by deadline | Ensure rest is taken but project is acceptable | Everything good so far with a little bit of caffiene

## Severity Table
Likelihood
|  | 1 | 2 | 3
Impact | 1 | Low | Low | Medium
| 2 | Low | Medium | High
| 3 | Medium | High | High

## Dropdowns
High
Medium
Low